## Project Plan
Tier | Phase | Activity | Sub-Activity | Description | Start Date | Due Date | Status
0 | Setup & Orientation | Project kickoff | Understand scope | As a team, read the main README and dashboard_template.md together. Align on what the starter code already does versus what is only a placeholder. Agree that the current dashboard is a starting point, not the final project. | 2026-01-15 | 2026-01-26 | Complete
0 | Setup & Orientation | Run all starter code | Verify local setup | Install requirements, download the data, run the EDA script, and launch the dashboard locally. Make sure everyone on the team can run the project end-to-end without errors. | 2026-01-15 | 2026-01-26 | Complete
0 | Data Access | StatsBomb ingestion | Local parquet loading | Matches, events, lineups loaded via Polars | 2026-01-15 | 2026-01-26 | Complete
0 | EDA | Data familiarity | Explore StatsBomb tables | Use the EDA script output to understand what data exists in matches, events, and lineups. Identify which columns are relevant for future metrics (timestamps, locations, teams, players, xG, etc.). | 2026-01-15 | 2026-01-26 | Complete
0 | EDA | Dataset exploration | Descriptive statistics | EDA script prints schema, distributions, ranges | 2026-01-15 | 2026-01-26 | Complete
0 | Dashboard Baseline | Understand current dashboard | Read dashboard_template.py | Walk through dashboard_template.py line by line. Understand how filters work, how callbacks are written, and how Polars filtering is done inside callbacks. | 2026-01-15 | 2026-01-26 | Complete
1 | Planning | Metric brainstorming | Choose analytics focus | Decide as a team which soccer analytics you want to focus on. Examples include possession chains, xG flow over time, defensive pressure (PPDA), or territorial dominance. Limit scope to 2–3 strong metrics rather than many shallow ones. | 2026-01-15 | 2026-01-18 | Not started
1 | Feature Engineering | Possession definition | Define possession rules | Research and agree on a clear definition of a possession (e.g., starts after ball recovery, ends on shot, foul, or turnover). Write this definition down so the logic is consistent across the team. | 2026-01-18 | 2026-01-22 | Not started
1 | Feature Engineering | Possession construction | Build possession IDs | Using the events table, assign a possession_id to each event based on your possession definition. This will likely involve sorting events by match and timestamp and detecting changes in team control. | 2026-01-20 | 2026-01-27 | Not started
1 | Feature Engineering | Possession summaries | Aggregate possession stats | Create a new table where each row is one possession. Compute simple stats such as possession duration, number of passes, number of shots, and ending event type. | 2026-01-20 | 2026-02-01 | Not started
1 | Feature Engineering | Possession stats | Aggregate metrics | Possession length, duration, shots | 2026-01-24 | 2026-02-01 | Not started
1 | Analytics | xG flow | Aggregate xG over time | For each match, compute cumulative xG by minute or by possession. This should allow you to show momentum swings throughout a match. | 2026-01-30 | 2026-02-05 | Not started
1 | Dashboard Extension | New visual | Add xG flow chart | Add a new chart to the dashboard that shows xG flow over time. Wire it into the existing filters so competition, season, and team selections update the chart. | 2026-02-04 | 2026-02-10 | Not started
1 | Dashboard | Drill-down | Match-level view | Select match → update charts | 2026-02-04 | 2026-02-12 | Not started
1 | Dashboard Extension | Match drilldown | Enable match selection | Add a dropdown or selector for individual matches. When a match is selected, update charts to show match-specific analytics rather than aggregates. | 2026-02-07 | 2026-02-15 | Not started
1 | Data Modeling | Intermediate tables | Reusable features | Derived Polars tables reused across charts | 2026-02-07 | 2026-02-15 | Not started
1 | Reporting | Midterm report | Write report | Architecture, metrics, screenshots | 2026-02-15 | 2026-02-25 | Not started
2 | Advanced Metrics | PPDA | Implement defensive pressure | Implement PPDA by counting opponent passes allowed in the defensive half per defensive action. Validate results by checking whether high-pressing teams have lower PPDA values. | 2026-02-20 | 2026-03-01 | Not started
2 | Advanced Metrics | Field tilt | Measure territorial dominance | Compute field tilt as the share of touches or passes in the attacking third. Aggregate by team and match to compare territorial control. | 2026-02-25 | 2026-03-06 | Not started
2 | Advanced Metrics | Progressive actions | Passes & carries | Distance-based progression logic | 2026-03-01 | 2026-03-10 | Not started
2 | Visualization | Pitch-based charts | Create spatial plots | Create shot maps or heatmaps using event location data. Overlay shots or passes on a soccer pitch to add spatial context. | 2026-03-05 | 2026-03-12 | Not started
2 | Architecture | Persistence | Caching layer | DuckDB or Parquet metric cache | 2026-03-08 | 2026-03-18 | Not started
2 | Architecture | Performance | Reduce repeated filtering | Refactor callbacks so heavy filtering or aggregations are not repeated unnecessarily. Consider precomputing derived tables once and reusing them. | 2026-03-08 | 2026-03-20 | Not started
3 | Architecture | Static artifacts | Precomputed bundles | Static dashboard mode | 2026-03-25 | 2026-04-03 | Not started
3 | Polish | Usability review | Improve readability | Review the dashboard as a user. Improve labels, titles, axis descriptions, and add brief explanatory text where charts may be confusing. | 2026-03-28 | 2026-04-01 | Not started
3 | Performance | Profiling | Measure speed and memory | Profile how long the dashboard takes to load and update. Document any optimizations you made and why they helped. | 2026-03-30 | 2026-04-05 | Not started
3 | UX | Refinement | Annotations | Add analytical context to charts | 2026-03-30 | 2026-04-05 | Not started
3 | Documentation | Final README | Usage & extension | How to run & extend project | 2026-04-01 | 2026-04-08 | Not started
3 | Final Reporting | Final report | Tell the story | Write the final report focusing on insights rather than code. Explain what the analytics reveal about teams or matches and what you learned building the system. | 2026-04-05 | 2026-04-15 | Not started